## Slide 1: BIT 286: Web Applications
Work Breakdown Structure (WBS); Scheduling

## Slide 2: Misc. Stuff For Mike To Remember 
Y'all got the feedback on the SRS, right?
  It was emailed out last Friday
  Can I just put everyone’s email on the To line?
    Talk to me privately if you don’t feel comfortable speaking up now
How much do y'all know about Git?
Note that Milestone #1 now has a web page
At the end of this lecture please hand in a piece of paper with feedback:
  What's going well in 286 so far?
  What could be improved?
  Name is optional

## Slide 3: Basically two parts:
Come up with a schedule
  Work Breakdown Structure
Track where you are on the schedule
  Use software to assist you
    (If nothing else, share the doc amongst everyone)

## Slide 4
From http://uweoconnect.extn.washington.edu/publicprojman04/

## Slide 5: Work Breakdown Structure (WBS)
Basic idea: break stuff down to small enough chunks that you can accurately predict how much time they’ll take
  Separate, non-overlapping tasks
  Each task should have the following 6 attributes:
    Status & completion is measurable
    Bounded
    Has a deliverable
    Time / cost can be accurately estimated
    Activity duration is reasonable
    Work assignments are independent
  Lowest tasks should start with verb, end with noun

## Slide 6: WBS
Also list necessary dependencies
  E.g., “I can’t start building the roof of the doghouse until the frame is in place, so ‘build the roof’ depends on ‘build the frame’ “
  E.g.,“create account page” depends on “define user account table in DB”
Also list the preferred sequence (the order you want to do stuff in)
  E.g., you could do the login page OR the password recovery page OR the create a new account page after the DB table is defined.
  You might choose to first do the ‘create new account’ then ‘login’ then ‘recover password’
  Even though you could really do them in any order

## Slide 7: Suggested approach for defining a WBS
Define how much time is 1 ‘quantum’
    An hour?
    A 2-hour block?
    A half-day?
  I’m guessing that since you’re students a 2 or 3 hour block is good starting point.
  Essentially you want to start something & get up to speed on what you need to do, do the task, and then wrap it up (update the schedule, email people, check in code, etc) in a single time quantum
Go through the Design Doc (from last week) and break things down into quanta.
As you’re doing that, list necessary dependencies & preferred sequence

## Slide 8: Track where you are on the schedule
In a ‘real’ project you’ll need to track where you are
  Budget (on software projects this is mostly personnel, so time == money)
  Are we behind?
  Are we ahead? Can we do some stuff on our ‘Wish List’?
  Your boss will want to know this stuff, possibly daily

## Slide 9: Let’s use software to assist us!
Excel
  Not really meant for graphically depicting the schedule…
  …BUT it’s really good at summing stuff up
  You can color-code stuff, and/or hide rows, which helps
  It looks like it’s pretty popular for this, probably because it’s already installed 
MS Project
  <quick demo here>
  I’m not an expert – you may or may not want to invest the time to get really good with this 
OSS clone of MS Project
  There’s a ton, and 15-20 minutes of Googling didn’t really reveal a clear leader
    Maybe LibreProject?